## Sheet1
CUSTOMER_NAME | Account No. | DEL_NO | SRF _NO | UNIQUE_ID | PRODUCT | Third party name | PO Date | CRDD Date | Partner RFS Date | PO to RFS | EDD ( If Pending) | Current Status | Delay Reasons (>5 Days from PO) | Skylink Remarks | PO Date | Partner RFS Date
SREE BALAJI INSTITUTE OF SCIENCE AND TECHNOLOGY |  | 44050049680 | 49680 | 49680 | Standard ILL | Skylink Multimedia PRIVATE LIMITED | 2025-07-28 | Update Pending | Update Pending |  |  | IR Received | Update Pending | Installed & IR received | 2025-07-28 | 2025-08-26
SUN X CONCRETE INDIA PRIVATE LIMITED |  | 44050061918 | 61918 | 61918 | Managed ILL | Skylink Multimedia PRIVATE LIMITED | 2025-01-10 | Update Pending | Update Pending |  | 2025-10-14 | Update Pending | Update Pending | Acceptance Awaited | 2025-10-01 | 2025-10-14
MULTI VISTA GLOBAL PVT LTD |  | 4405836626 | 60342 | 60342 | Standard ILL | Skylink Multimedia PRIVATE LIMITED | Update Pending | Update Pending | Update Pending |  | Update Pending | Update Pending | Update Pending | Acceptance Awaited | 2025-09-22 | 2025-10-09
PIXEL BOY MEDIA PUBLICITIES PRIVATE LIMITED |  | 44050060388 | 60388 | 60388 | Secured ILL | Skylink Multimedia PRIVATE LIMITED | 2025-09-24 | Update Pending | Update Pending |  | 2025-10-17 | Update Pending | Due to metro work longer route taken for which we needed time to take Management approval | Acceptance Awaited | 2025-09-24 | 2025-10-18
RIP IT SOLUTIONS PRIVATE LIMITED |  | 44050014851 | 60666 | 60666 | Standard ILL | Skylink Multimedia PRIVATE LIMITED | Update Pending | Update Pending | Update Pending |  | Update Pending | Update Pending | Update Pending | Acceptance Awaited | 2025-09-23 | 2025-10-10
TAGORE EDUCATIONAL TRUST |  | 44050057177 | 57177 | 57177 | Standard ILL | Skylink Multimedia PRIVATE LIMITED | 2025-09-25 | Update Pending | Update Pending |  | 2025-09-10 | Update Pending | Delay from Partner in arranging materials | Acceptance Awaited | 2025-09-25 | 2025-10-09
EQUITAS SMALL FINANCE BANK LIMITED |  | 422050058739 | 58739 | 58739 | Standard ILL | Skylink Multimedia PRIVATE LIMITED | 2025-09-17 | Update Pending | 2025-09-24 | 7 |  | Acceptance Awaited | Update Pending | Acceptance Awaited | 2025-09-17 | 2025-09-24
THE MADRAS SEVA SADAN |  | 44050043880 | 43880 | 43880 | Secured ILL | Skylink Multimedia PRIVATE LIMITED | 2025-06-11 | Update Pending | Update Pending |  |  | Update Pending | customer site not ready | IBD Done, Site not ready | 2025-06-11 | Site not ready
BL FINPRO |  | 4465131500 | 59766 | 4465131500 | SIP Trunk | Skylink Multimedia PRIVATE LIMITED | Update Pending | Update Pending | Update Pending |  |  | IR Received | Update Pending | NA
AHAM HOUSING FINANCE LIMITED | 922712512 | 4465130500 | 57489 | 4465130500 | SIP Trunk | Skylink Multimedia PRIVATE LIMITED | Update Pending | Update Pending | Update Pending |  |  | Update Pending | Update Pending | Acceptance Awaited | 2025-09-02 | 2025-09-11
ALACRIY NET SYSTEM SERVICE PRIVATE LIMITED | 922704102 | 4166512000 | 52911 | 4166512000 | SIP Trunk | Skylink Multimedia PRIVATE LIMITED | Update Pending | Update Pending | Update Pending |  |  | Update Pending | TTL Pendenc | TTSL Pendency
SREE BALAJI INSTITUTE OF SCIENCE AND TECHNOLOGY | 922655036 | 4469009600 | 49681 | 4469009600 | SIP Trunk | Skylink Multimedia PRIVATE LIMITED | 2025-07-28 | Update Pending | Update Pending |  |  | IR Received | Update Pending | Installed & IR received | 2025-07-28 | 2025-08-26