## L2
Sl. No. | Lead ID | Customer Name | Title | Status | Accepted By | Action | Task Pending Days | Zone TL | Status
1 | 3971 | TATA | Tata : SUN X CONCRETE INDIA PRIVATE LIMITED - Ponnamalle | L2 Survey | Nagalakshmi Gunaseelan |  | 1 Days | Murugesan G | New | New | Survey WIP
2 | 3970 | Power Grid Teleservices Limited - HYD | PGCL - RCI side gate Chamber To Chess Back Gate, Kurmalguda, Hyderabad, Telangana (GEM-SCH-7) | L2 Survey | Nanda Kumar |  | 2 Days | Kusa Karnakar | New | New
3 | 3969 | Power Grid Teleservices Limited - HYD | PGCL - RCI side gate Chamber To TS TRANSCO 400 KV SUB STATION, Mamidipally, Hyderabad, Telangana (GEM-SCH-6) | L2 Survey | Nanda Kumar |  | 2 Days | Kusa Karnakar | New | New
4 | 3968 | Power Grid Teleservices Limited - HYD | PGCL - ASL Chamber Hafiz Baba Nagar to PGCIL Chamber DERL/DLRL - Hyderabad, Telangana (GEM-SCH-5) | L2 Survey | Nanda Kumar |  | 2 Days | Kusa Karnakar | New | New
5 | 3967 | Power Grid Teleservices Limited - HYD | PGCL - ASL Chamber Hafiz Baba Nagar to TS Transco 220 KV Sub Station - Hyderabad, Telangana (GEM-SCH-4) | L2 Survey | Nanda Kumar |  | 2 Days | Kusa Karnakar | New | New
6 | 3966 | Power Grid Teleservices Limited - HYD | PGCL - DGMSS Gate Chamber to Chess Back Gate, Kurmalguda, Hyderabad, Telangana (GEM-SCH-2) | L2 Survey | Nanda Kumar |  | 2 Days | Kusa Karnakar | New | New
7 | 3965 | Power Grid Teleservices Limited - HYD | PGCL - DGMSS Gate Chamber to TSTransco 220KV Chandrayan gutta - Hyderabad, Telangana (GEM-SCH-1) | L2 Survey | Nanda Kumar |  | 2 Days | Kusa Karnakar | New | New
8 | 3964 | TIkona | Tikona - Chinnamal Balu to Swetha Towers | L2 Survey | Nagalakshmi Gunaseelan |  | 4 Days | Santhosh V | Open | Hold by Client
9 | 3963 | TIkona | Tikona - VGN La Prasine To Axis Bank - Nolambur | L2 Survey | Nagalakshmi Gunaseelan |  | 4 Days | Murugesan G | Open | Lat/Long wrong. To be taken up with Client
10 | 3962 | Bharti Airtel Ltd - Tamil Nadu | Airtel - HL MANDO ANAND INDIA PRIVATE LIMITED - Kanchipuram, Tamil Nadu (RA 2730974), Chengalpet | L2 Survey | Nanda Kumar |  | 4 Days | Murugesan G | Open | Survey WIP
11 | 3961 | INFYNIX COMMUNICATIONS LIMITED | Infynix - 1005250721 - IT PARK SIRUSERI NAVALLUR POST - Chennai, Tamil Nadu | L2 Survey | Nanda Kumar |  | 8 Days | Murugesan G | Open | Survey WIP
12 | 3960 | INFYNIX COMMUNICATIONS LIMITED | Infynix - First source-F001610 - Kancheepuram, Tamil Nadu | L2 Survey | Nanda Kumar |  | 8 Days | Murugesan G | Open | Alternate BTS to be confirmed by Client
13 | 3959 | Bharti Airtel Ltd - Kerala | Airtel - Moss Adams India LLP - Cochin, Kerala (RA 2737964) | L2 Survey | Nanda Kumar |  | 8 Days | Hijas E H | Open | Hold by Client
14 | 3958 | Bharti Airtel Ltd - Tamil Nadu | Airtel - GULF OIL LUBRICANTS INDIA LIMITED - Chennai, Tamil Nadu (RA 2732216) | L2 Survey | Nanda Kumar |  | 8 Days | Murugesan G | Open | Vendor to be finalised
15 | 3957 | Bharti Airtel Ltd - Tamil Nadu | Airtel - Sri Shanmugha Educational Charitable Trust - SALEM, TAMIL NADU (RA 2725843) | L2 Survey | Nanda Kumar |  | 8 Days | Thiruppathi Raja D | Open | Survey WIP
16 | 3947 | Bharti Airtel Ltd - Kerala | Airtel - ARINC - Expereo International BV - Ernakulam, Kerala (RA 4936206) | L2 Survey | Nanda Kumar |  | 11 Days | Hijas E H | Open | Hold by Client
17 | 3946 | Vodafone Idea Limited | Vodafone Idea - US TECHNOLOGY - Peelamedu, Coimbatore (FR02813842) | L2 Survey | Nanda Kumar |  | 11 Days | Thiruppathi Raja D | Open | SNR
18 | 3945 | Bharti Airtel Ltd - Kerala | Airtel - CARBORUNDUM UNIVERSAL LIMITED - KOTTAYAM, KERALA (Via Email) | L2 Survey | Nanda Kumar |  | 12 Days | Hijas E H | Open | Survey WIP
19 | 3944 | Bharti Airtel Ltd - Kerala | Airtel - CARBORUNDUM UNIVERSAL LIMITED - THRISSUR, KERALA (Via Email) | L2 Survey | Nanda Kumar |  | 12 Days | Hijas E H | Open | Vendor to be finalised
20 | 3938 | Bharti Airtel Ltd - Telangana | Airtel - Virginia Transformer India Private Limited - Hyderabad, Telangana (RA 2671986) | L2 Survey | Nanda Kumar |  | 15 Days | Kusa Karnakar | Open | Hold by Client
21 | 3936 | Bharti Airtel Ltd - Telangana | Airtel - ls and wjv - mekaguda, nandigama mandal - Ranga Reddy, Telangana (RA 2695442) | L2 Survey | Nanda Kumar |  | 15 Days | Kusa Karnakar | Open | Hold by Client
22 | 3935 | RELINACE JIO INFOCOMM LTD | Jio : MOTHERSON SUMI SYSTEMS LIMITED - Kancheepuram (Secondary) | L2 Survey | Nagalakshmi Gunaseelan |  | 17 Days | Murugesan G | Open | Survey WIP
23 | 3934 | RELINACE JIO INFOCOMM LTD | Jio : MOTHERSON SUMI SYSTEMS LIMITED - Kancheepuram (Primary) | L2 Survey | Nagalakshmi Gunaseelan |  | 17 Days | Murugesan G | Open | Survey WIP
24 | 3933 | INFYNIX COMMUNICATIONS LIMITED | Infynix - 25C062894 - Ankenpally Plant - Medak, Hyderabad, Telangana | L2 Survey | Nanda Kumar |  | 17 Days | Kusa Karnakar | Open | Access pending
25 | 3924 | TIkona | Tikona : Delta Electronics India Private Limited - Krishnagiri | Yet To Start - Customer Dependency | Nagalakshmi Gunaseelan |  | 13 Days | Prabhakaran M | Open | Hold by Client. Mail sent
26 | 3911 | TATA | TATA : ALLIANT TECHNOLOGIES - Salem | Yet To Start - Customer Dependency | Nagalakshmi Gunaseelan |  | 18 Days | Thiruppathi Raja D | Open | Hold by Client
27 | 3898 | Bharti Airtel Ltd - Karnataka | Airtel - RELIANCE BP MOBILITY LIMITED - Belagavi, Karnataka (RA 2670404) | L2 Survey | Nanda Kumar |  | 38 Days | B Sanna Veerabadrachar B | Open | SLA - To be made lenient. Under Discussion
28 | 3876 | Bharti Airtel Ltd - Tamil Nadu | Airtel - Deloitte - Coimbatore, TAMIL NADU (via Email) | L2 Survey | Nanda Kumar |  | 46 Days | Thiruppathi Raja D | Open | Hold by Client
29 | 3874 | Bharti Airtel Ltd - Telangana | Airtel - OUTAMATION TECHNOLOGIES PRIVATE LIMITED - Hyderabad, Telangana (RA 2568844) | L2 Survey | Nanda Kumar |  | 46 Days | Kusa Karnakar | Open | SNR-Access pending
30 | 3872 | Bharti Airtel Ltd - Karnataka | Airtel - Arrow Electronics India Pvt Ltd - Mysuru, Karnataka (RA 2663163) | L2 Survey | Nanda Kumar |  | 49 Days | B Sanna Veerabadrachar B | Open | SNR-Access pending
31 | 3856 | TATA | Tata : ALACRIY NET SYSTEM SERVICE PRIVATE LIMITED - Vellore | Yet To Start - Customer Dependency | Nagalakshmi Gunaseelan |  | 32 Days | Prabhakaran M | Open | Hold by Client
32 | 3731 | Bharti Airtel Ltd - Tamil Nadu | Airtel - Sai University - Paiyanur, Tamil Nadu (Via Email) | L2 Survey | Nanda Kumar |  | 76 Days | Vignesh Pichandi | Open | Hold by Client
33 | 3697 | Vodafone Idea Limited | Vodafone Idea - UST Chennai - Chennai, Tamilnadu | L2 Survey | Nanda Kumar |  | 90 Days | Vignesh Pichandi | Open | SNR
34 | 3694 | Bharti Airtel Ltd - Andhra Pradesh | Airtel - UBER INDIA SYSTEMS PRIVATE LIMITED - Visakhapatnam, Andhra Pradesh (RA 2561672) | L2 Survey | Nanda Kumar |  | 92 Days | Ballamudi Anand Kumar | Open | Hold by Client
35 | 3688 | Bharti Airtel Ltd - Puducherry | Airtel - ITRANSZ FTTX PRIVATE LIMITED - Karaikal, Puducherry (RA 2569968) | L2 Survey | Nanda Kumar |  | 95 Days | Prabhakaran M | Dropped | Dropped

## Acq
Sl. No. | Lead ID | Customer Name | Title | Status | Action | Task Pending Days | Status
1 | 3953 | TATA | Tata : PIXEL BOY MEDIA PUBLICITIES PRIVATE LIMITED - Mylapore (Secondary) | Awaiting PO |  | 7 Days | Open | Revised Quote to be subitted
2 | 3952 | TATA | Tata : PIXEL BOY MEDIA PUBLICITIES PRIVATE LIMITED - Mylapore (Primary) | Awaiting PO |  | 7 Days | Open
3 | 3951 | Vodafone Idea Limited | Vodafone Idea - Uddanapalli Village, Hosur - Krishnagiri, Tamil Nadu (FR02816667) | Awaiting PO |  | 6 Days | Open
4 | 3950 | Vodafone Idea Limited | Vodafone Idea - BESTMANAHALLI - ANEKAL, BENGALURU, KARNATAKA (FR02815971) | Awaiting PO |  | 6 Days | Open
5 | 3941 | Sify Technologies Ltd - Tamil Nadu | Sify : HDFC Bank - Krishnagiri (Secondary) | Awaiting PO |  | 8 Days | Open
6 | 3940 | Sify Technologies Ltd - Tamil Nadu | Sify : HDFC Bank - Krishnagiri (Primary) | Awaiting PO |  | 8 Days | Open
7 | 3937 | Vodafone Idea Limited | Vodafone Idea - Millenia Business Park To PSA Fort - Chennai, Tamil Nadu (FR02807699) | Awaiting PO |  | 6 Days | Open
8 | 3932 | Bharti Airtel Ltd - Telangana | Airtel - Corpus Software Private Limited (CORPUS ENTERPRISES PRIVATE LIMITED) - MEDAK, Telangana (RA 2720228) | Awaiting PO |  | 14 Days | Open
9 | 3929 | Vodafone Idea Limited | Vodafone Idea - Brakes - Shoolagiri, Krishnagiri, Tamil Nadu (FR02806542) | Awaiting PO |  | 15 Days | Open
10 | 3926 | TATA | Tata : SURYODAY SMALL FINANCE BANK LIMITED - Keelkattalai | PO Received |  | 23 Days | Open
11 | 3920 | INFYNIX COMMUNICATIONS LIMITED | Infynix - 1005250703 Fortune Enclave - Hyderabad, Telangana | Awaiting PO |  | 25 Days | Open | Revised PO Awiated
12 | 3917 | TIkona | Tikona : ENT_WM Global Technology Services India Private Limited - Zamin Pallavaram | Awaiting PO |  | 30 Days | Open
13 | 3916 | Bharti Airtel Ltd - Karnataka | Airtel - INDO MIM LIMITED - KIADB Industrial Area - Doddaballapura, Bengaluru, Karnataka (RA 2683683) | PO Received |  | 8 Days | Open | Under PAWS
14 | 3901 | Bharti Airtel Ltd - Tamil Nadu | Airtel - GCXG INDIA PRIVATE LIMITED (High Glory Footwear India Private Limited) - Kallakurichi, Tamil Nadu (RA 2676843) | Awaiting PO |  | 18 Days | Open
15 | 3899 | Bharti Airtel Ltd - Karnataka | Airtel - RELIANCE BP MOBILITY LIMITED - Dharwad, Karnataka (RA 2669744) | Awaiting PO |  | 9 Days | Open
16 | 3897 | Bharti Airtel Ltd - Karnataka | Airtel - INDO MIM LIMITED - Obedenahalli Industrial Area - Bengaluru Rural, Karnataka (RA 2676348) | Awaiting PO |  | 21 Days | Open
17 | 3893 | Bharti Airtel Ltd - Karnataka | Airtel - Hollingsworth & Vose - H&V ADVANCED MATERIALS (INDIA) PRIVATE LIMITED - Mysuru, Karnataka (RA 2669361) | Awaiting PO |  | 17 Days | Open
18 | 3886 | Bharti Airtel Ltd - Karnataka | Airtel - HGC Global Communications (cmi.chinamobile.com) - Devanahalli, Bengaluru Rural District, Karnataka (RA 4930568) | Awaiting PO |  | 6 Days | Open
19 | 3885 | Bharti Airtel Ltd - Tamil Nadu | Airtel - INNOVATIVE WORK SOLUTIONS - Tirunelveli, TAMIL NADU (RA 2664720) | Awaiting PO |  | 36 Days | Open | Hold by Client
20 | 3877 | Bharti Airtel Ltd - Andhra Pradesh | Airtel - CR HEALTH CARE SERVICES PVT LTD - East Godavari, Andhra Pradesh (RA 2664840) | Awaiting PO |  | 27 Days | Open
21 | 3844 | Bharti Airtel Ltd - Kerala | Airtel - RELIANCE BP MOBILITY LIMITED - Ernakulam, Kerala (RA 2395761) | Awaiting PO |  | 46 Days | Open
22 | 3745 | Nivid Telecom | Nivid Telecom - Sholinganallur Perumbakkam To Nivid Perumbakkam POP - Chennai, Tamil Nadu | PO Received |  | 49 Days | Open | Hold by Client
23 | 3744 | Nivid Telecom | Nivid Telecom - Kuppam Road Valmiki Nagar To Nivid Thiruvanmiyur POP - Chennai, Tamil Nadu | Awaiting PO |  | 64 Days | Open
24 | 3743 | Bharti Airtel Ltd - Tamil Nadu | Airtel - Resolux India Pvt Ltd - Thiruvallur, Tamil Nadu (Via Email) | Awaiting PO |  | 46 Days | Open
25 | 3740 | Nivid Telecom | Nivid Telecom - NPL Devi To Millenia Business Park - Chennai, Tamil Nadu | Awaiting PO |  | 64 Days | Open
26 | 3730 | INFYNIX COMMUNICATIONS LIMITED | Infynix - Guindy Thiru Vi Ka Industrial Estate To Phase 2 SIDCO Industrial Estate - Chennai, Tamil Nadu | Awaiting PO |  | 64 Days | Open
27 | 3701 | POWERGRID TELESERVICES LIMITED - TAMILNADU | PGCL - Zoho Estancia IT Park - SRM Data Centre - Kattankulathur, Tamil Nadu (GEM-SCH-17) | PO Received |  | 88 Days | Open | To be moved to Installation
28 | 3679 | POWERGRID TELESERVICES LIMITED - TAMILNADU | PGCL - Jio Star Kochar Jade - Manhole HTL Grounds - Guindy (GEM-SCH-2) | PO Received |  | 99 Days | Open
29 | 3675 | Bharti Airtel Ltd - Tamil Nadu | Airtel - BSF Design Solutions India Private Limited - Chennai, Tamil Nadu (via Email) | Awaiting PO |  | 99 Days | Dropped | No response from Client
30 | 3635 | Bharti Airtel Ltd - Tamil Nadu | Airtel - THE MELVISHARAM MUSLIM EDUCATIONAL SOCIETY - Vellore, Tamilnadu (via Email) | Awaiting PO |  | 106 Days | Open | Hold by Client
31 | 3625 | Bharti Airtel Ltd - Telangana | Airtel - GTT (GB) - Fossil India Pvt Ltd (RA 2497940) | Awaiting PO |  | 121 Days | Open | Hold by Client

## Installation
Sl. No. | Lead ID | Customer Name | Title | Status | Task Pending Days | Delivery Pending Days | Logs | IC | Status | EDD
1 | 3956 | TATA | Tata : TAGORE EDUCATIONAL TRUST - Tambaram BTS (Secondary) | Material Request | 0 Days | 9 Days |  | Murugesan | Open | Material in Transit
2 | 3955 | TATA | Tata : TAGORE EDUCATIONAL TRUST - Chrompet BTS (Primary) | Material Request | 5 Days | 9 Days |  | Murugesan | Open | Material in Transit
3 | 3949 | TATA | Tata : RIP IT SOLUTIONS PRIVATE LIMITED - Kottivakkam (Secondary) | Material Request | 1 Days | 10 Days |  | Murugesan | Open | Material in Transit
4 | 3948 | TATA | Tata : RIP IT SOLUTIONS PRIVATE LIMITED - Kottivakkam (Primary) | Material Request | 1 Days | 10 Days |  | Murugesan | Open | Material in Transit
5 | 3943 | TATA | TATA : MULTI VISTA GLOBAL PVT LTD - Maduravoyal (Secondary) | Material Request | 0 Days | 12 Days |  | Murugesan | Open | Material in Transit
6 | 3942 | TATA | TATA : MULTI VISTA GLOBAL PVT LTD - Maduravoyal (Primary) | Material Request | 0 Days | 12 Days |  | Murugesan | Open | Material in Transit
7 | 3939 | Powergrid Teleservices Limited - Vijayawada | PGCL - TATA COMMUNICATIONS LTD, RBI Stalin Central To SIFY CVR CHAMBERS - Vijayawada, Andhra Pradesh (GEM-SCH-2) | Installation Work In Progress | 3 Days | 14 Days |  | Naren | Open | WIP | 2025-10-04
8 | 3930 | TATA | Tata : EQUITAS SMALL FINANCE BANK LIMITED - Coimbatore | Installation Work In Progress | 10 Days | 19 Days |  | Sibi | Open | To be moved to Acceptance
9 | 3925 | Bharti Airtel Ltd - Kerala | Airtel - KPMG ASSURANCE AND CONSULTING SERVICES LLP - SECONDARY PATH - Ernakulam, Kerala (RA 2669477) | Material Procurement | 6 Days | 28 Days |  | Sibi | Open | Material in Transit
10 | 3910 | RELINACE JIO INFOCOMM LTD | Jio: Sify Technologies Limited - Nandanam | Installation Work In Progress | 11 Days | 33 Days |  | Murugesan | Open | Awaiting customer end permission
11 | 3895 | RELINACE JIO INFOCOMM LTD | Jio : Amazon Seller Services Private Limited - Karnataka | Material Procurement | 6 Days | 39 Days |  | Naren | Open | Material in Transit
12 | 3878 | TATA | Tata : Hyundai Kefico India Private Limited - Sriperumbudur | Material Request | 1 Days | 45 Days |  | Murugesan | Open | Awaiting Material. Materail by 6th Oct
13 | 3870 | POWERGRID TELESERVICES LIMITED - KERALA | PGCL - PG MH DPI To Regional Ayurveda Research Institute - Thiruvananthapuram, Kerala (GEM-SCH-5) | Material Procurement | 6 Days | 50 Days |  | Sibi | Open | Customer access pending
14 | 3869 | POWERGRID TELESERVICES LIMITED - KERALA | PGCL - Regional Ayurveda Research Institute To Army Pangode - Thiruvananthapuram, Kerala (GEM-SCH-4) | Material Procurement | 6 Days | 50 Days |  | Sibi | Open | Customer access pending
15 | 3868 | POWERGRID TELESERVICES LIMITED - KERALA | PGCL - Army Pangode To ISRO Inertial Systems Unit - Thiruvananthapuram, Kerala (GEM-SCH-3) | Material Dispatched | 4 Days | 50 Days |  | Sibi | Open | WIP
16 | 3867 | POWERGRID TELESERVICES LIMITED - KERALA | PGCL - ISRO Inertial Systems Unit To PG MH near CDAC - Thiruvananthapuram, Kerala (GEM-SCH-2) | Installation Work In Progress | 6 Days | 50 Days |  | Sibi | Open | WIP
17 | 3866 | POWERGRID TELESERVICES LIMITED - KERALA | PGCL - PG MH near CDAC To Army Pangode - Thiruvananthapuram, Kerala (GEM-SCH-1) | Installation Work In Progress | 14 Days | 50 Days |  | Sibi | Open | WIP
18 | 3860 | TATA | Tata : THE MADRAS SEVA SADAN - T. Nagar | Installation Work In Progress - CSD | 22 Days | 51 Days |  | Murugesan | Open | Customer site Not Ready
19 | 3749 | Bharti Airtel Ltd - Tamil Nadu | Airtel - PRICOL PRECISION PRODUCTS PRIVATE LIMITED - Krishnagiri, Tamil Nadu (RA 2695388) | Installation Work In Progress | 10 Days | 65 Days |  | Sibi | Open | To be moved to acceptance
20 | 3747 | MICROSENSE | Microsense - Sify IDC - Chennai, Tamil Nadu (Via Email - For Shifting) | Material Request | 44 Days | 66 Days |  | Murugesan | Open | To be moved to Acceptance
21 | 3691 | INFYNIX COMMUNICATIONS LIMITED | Infynix - 25E332974 - Paiyanur, Kadambadi | Material Dispatched | 3 Days | 94 Days |  | Murugesan | Open | WIP
22 | 3678 | Bharti Airtel Ltd - Andhra Pradesh | Airtel - BT global Communications India Private Limited [BT(GB)] - VIJAYAWADA, Andhra Pradesh (RA 2552956) | Installation Work In Progress | 16 Days | 100 Days |  | Naren | Open | Customer end permission awaited
23 | 3658 | RELINACE JIO INFOCOMM LTD | Jio: BSNL CBIC - Pondicherry | Installation Work In Progress | 4 Days | 108 Days |  | Murugesan | Open | To be connectedto Chamber & Chamber not ready
24 | 3597 | POWERGRID TELESERVICES LIMITED - TAMILNADU | PGCL - Chamber Opp. Bsnl - Shyam Spectra Pvt - Chennai (GEM-SCH-1) | Installation Work In Progress - CSD | 83 Days | 136 Days |  | Murugesan | Open | IBD/OH Completed. Splicing pending
25 | 3591 | Bharti Airtel Ltd - Telangana | Airtel - Anurag Engineering College - Telangana (RA 2687981) | Installation Work In Progress | 15 Days | 140 Days |  | Naren | Open | Work to be resumed after Holidays
26 | 3523 | RELINACE JIO INFOCOMM LTD | Jio - BSNL-CBIC - Anna Nagar | Installation Work In Progress - CSD | 22 Days | 175 Days |  | Murugesan | Open | To be connectedto Chamber & Chamber not ready

## Acceptance
Sl. No. | Lead ID | Customer Name | Title | Status | Task Pending Days | Delivery Pending Days | Logs | Status
1 | 3918 | TATA | Tata : AHAM HOUSING FINANCE PRIVATE LIMITED - T. Nagar (Secondary) | IR Pending | 22 Days | 31 Days |  | Open
2 | 3914 | TATA | Tata : AHAM HOUSING FINANCE PRIVATE LIMITED - T. Nagar (Primary) | IR Pending | 22 Days | 32 Days |  | Open
3 | 3908 | TIkona | Tikona : Hameedia Complex to Prince Towers - Triplicane to Nungambakkam | IR Pending | 16 Days | 35 Days |  | Open
4 | 3862 | TATA | Tata : SREE BALAJI INSTITUTE OF SCIENCE AND TECHNOLOGY - Tambaram BTS (Secondary) | IR Pending | 38 Days | 51 Days |  | Open
5 | 3861 | TATA | Tata : SREE BALAJI INSTITUTE OF SCIENCE AND TECHNOLOGY - Chrompet BTS (Primary) | IR Pending | 38 Days | 51 Days |  | Open
6 | 3854 | TATA | Tata : MUTHURAMALINGAM KUNCHARAVALLI EDUCATIONAL TRUST - Path 4 - V kids West To Velammal Vidayalaya West | IR Pending | 32 Days | 56 Days |  | Open
7 | 3852 | TATA | Tata : MUTHURAMALINGAM KUNCHARAVALLI EDUCATIONAL TRUST - Path 2 - Vkids T S K To Velammal JR KG | IR Pending | 46 Days | 56 Days |  | Open
8 | 3851 | TATA | Tata : MUTHURAMALINGAM KUNCHARAVALLI EDUCATIONAL TRUST - Path 1 - BTS to Vkids T S K | IR Pending | 46 Days | 56 Days |  | Open
9 | 3850 | Bharti Airtel Ltd - Kerala | Airtel - KPMG ASSURANCE AND CONSULTING SERVICES LLP - Ernakulam, Kerala (RA 2653051) | IR Pending | 15 Days | 57 Days |  | Open
10 | 3847 | Bharti Airtel Ltd - Karnataka | Airtel - RELIANCE BP MOBILITY LIMITED - Mandya, Karnataka (RA 2579047) | IR Pending | 16 Days | 59 Days |  | Open
11 | 3843 | Bharti Airtel Ltd - Tamil Nadu | Airtel - FINECONS PRIVATE LIMITED - Pudukkottai, Tamil Nadu (RA 4930639) | IR Pending | 8 Days | 59 Days |  | Open
12 | 3756 | Bharti Airtel Ltd - Kerala | Airtel - UNION BANK OF INDIA - Kottayam, Kerala (RA 2638664) | IR Pending | 14 Days | 61 Days |  | Open
13 | 3755 | Bharti Airtel Ltd - Andhra Pradesh | Airtel - RELIANCE BP MOBILITY LIMITED - WEST GODAVARI, ANDHRA PRADESH (RA 2638789) | IR Pending | 8 Days | 63 Days |  | Open
14 | 3753 | Bharti Airtel Ltd - Karnataka | Airtel - Vega Auto Accessories Pvt Ltd - Belgaum, Karnataka (RA 2637616) | IR Pending | 32 Days | 64 Days |  | Open
15 | 3736 | Bharti Airtel Ltd - Tamil Nadu | Airtel - Imperial Auto Industries Ltd - TIRUVALLUR, Tamil Nadu (RA 2620261) | IR Pending | 22 Days | 72 Days |  | Open
16 | 3732 | Bharti Airtel Ltd - Karnataka | Airtel - B T P INFO SERVE PVT LTD - Belagavi, Karnataka (RA 2607857) | IR Pending | 36 Days | 73 Days |  | Open
17 | 3728 | INFYNIX COMMUNICATIONS LIMITED | Infynix - 25C292883 / 25D292942 STT Global Data Centre TATA Communications To Global Infocity Park - Chennai, Tamil Nadu | IR Pending | 23 Days | 79 Days |  | Open
18 | 3727 | VIVA | VIVA - Gee Gee Emerald Towers To Reliance House - Chennai, Tamil Nadu | IR Pending | 31 Days | 80 Days |  | Open
19 | 3695 | Bharti Airtel Ltd - Andhra Pradesh | Airtel - Indi Village Tech Solutions LLP - Yemmiganur, KURNOOL, ANDHRA PRADESH (RA 2563885) | IR Pending | 11 Days | 92 Days |  | Open
20 | 3507 | Bharti Airtel Ltd - Andhra Pradesh | Airtel - HINDUSTAN AGRO PRODUCTS LTD - Machavaram, AP (RA 2153546) | IR Pending | 11 Days | 193 Days |  | Open

## Vesta
Sl. No. | Lead ID | Title | Location | Find Date | Created By | Action | Remarks on 4/10
1 | 3962 | Airtel - HL MANDO ANAND INDIA PRIVATE LIMITED - Kanchipuram, Tamil Nadu (RA 2730974) | Kancheepuram | 2025-09-30 14:55 | Nanda Kumar | open | Not Finalised. Planned to visit Kanchi on 6/10.
2 | 3961 | Infynix - 1005250721 - IT PARK SIRUSERI NAVALLUR POST - Chennai, Tamil Nadu |  | 2025-09-26 17:14 | Nanda Kumar | open | Internal Team. Case to be moved back to Galileo
3 | 3960 | Infynix - First source-F001610 - Kancheepuram, Tamil Nadu | Kancheepuram | 2025-09-26 15:35 | Nanda Kumar | open | Not Finalised. Planned to visit Kanchi on 6/10.
4 | 3959 | Airtel - Moss Adams India LLP - Cochin, Kerala (RA 2737964) | Cochin | 2025-09-26 11:18 | Nanda Kumar | open | Identified new vendor. Onboarding under progress. 7/10
5 | 3958 | Airtel - GULF OIL LUBRICANTS INDIA LIMITED - Chennai, Tamil Nadu (RA 2732216) | Chennai | 2025-09-26 10:47 | Nanda Kumar | open | Not Finalised. Loganathan to speak to Rajesh and his concurrence
6 | 3950 | Vodafone Idea - BESTMANAHALLI - ANEKAL, BANGALORE, KARNATAKA |  | 2025-09-24 11:11 | Nanda Kumar | open | Not Finalised. TL's visit planned on 6/10
7 | 3947 | Airtel - ARINC - Expereo International BV - Ernakulam, Kerala (RA 4936206) | Ernakulam | 2025-09-23 18:06 | Nanda Kumar | open | Identified new vendor. Onboarding under progress. 7/10
8 | 3946 | Vodafone Idea - US TECHNOLOGY - Peelamedu, Coimbatore (FR02813842) | Coimbatore | 2025-09-23 10:47 | Nanda Kumar | open | Vendor Identified. Document pending. TL is following it .
9 | 3945 | Airtel - CARBORUNDUM UNIVERSAL LIMITED - KOTTAYAM, KERALA (Via Email) | Kottayam | 2025-09-22 19:55 | Nanda Kumar | open | Not finalised. TL's visit to be planned
10 | 3934 | Jio : MOTHERSON SUMI SYSTEMS LIMITED - Kancheepuram (Primary) | Kancheepuram | 2025-09-17 17:03 | Nagalakshmi Gunaseelan | open | Not Finalised. Planned to visit Kanchi on 6/10.
11 | 3931 | Infynix - 1003250605 - Electronic Hardware - Sriperumbudur, Tamil Nadu | Sriperumbudur | 2025-09-16 10:43 | Nanda Kumar | open | Not Finalised. Planned to visit Kanchi on 6/10.
12 | 3886 | Airtel - HGC Global Communications (cmi.chinamobile.com) - Devanahalli, Bengaluru Rural District, Karnataka (RA 4930568) | Devanhalli | 2025-09-11 19:58 | Nanda Kumar | open | Not Finalised. TL's visit planned on 6/10
13 | 3900 | Airtel - SONY INDIA PRIVATE LIMITED (Flyjac Logistics Pvt Ltd) - Ernakulam, Kerala (RA 4921444) | Ernakulam | 2025-09-03 15:45 | Nanda Kumar | open | Identified new vendor. Onboarding under progress. 7/10
14 | 3898 | Airtel - RELIANCE BP MOBILITY LIMITED - Belagavi, Karnataka (RA 2670404) | Belagavi | 2025-09-01 14:21 | Nanda Kumar | open | SLA to be made lenient with the Client
15 | 3752 | Airtel - Aspinwall and Company Limited - Cochin, Kerala (RA 2637463) | Cochin | 2025-08-22 11:39 | Nanda Kumar | open | Vendor Finalised. Case t be moved to Galileo
16 | 3884 | Airtel - MINERA STEEL AND POWER PRIVATE LIMITED - Bellary, Karnataka (RA 2634526) | Belluru | 2025-08-21 14:25 | Nanda Kumar | open | Not Finalised.
17 | 3880 | Account EQUITAS SMALL FINANCE BANK LIMITED Opportunity ID 20660705 ILL 10 mbps, Karur |  | 2025-08-20 12:51 | Nagalakshmi Gunaseelan | open | Vendor Identified. Document pending. TL is following it .
18 | 3743 | Airtel - Resolux India Pvt Ltd - Thiruvallur, Tamil Nadu (Via Email) | Thiruvallur | 2025-08-08 18:23 | Nanda Kumar | open | Vendor Interested. Feedback awaited by 6/10
19 | 3689 | Airtel - THE KARUR VYSYA BANK LTD - ONGOLE - PRAKASAM DISTRICT, ONGOLE, AP (RA 2553157) | Prakasam | 2025-08-03 13:16 |  | open | SNC done laying and O&M vendor yet t be finalised.